## Sheet1
ID | STATUS | PRIORITY | TASK | PERSON | Done% | Category
1 | Rezolved | High | project plan | Ligia | 100 | Planning | High
2 | Rezolved | Medium | use cases | Ligia | 100 | Planning | Medium
3 | Rezolved | Medium | create project in git | Navid | 100 | Planning | Low
4 | Rezolved | High | database model | Navid | 100 | Planning
5 | Rezolved | High | url model | Navid | 100 | Planning | New
6 | Rezolved | High | UI Sketching | Ligia/Navid | 100 | Planning | In progress
7 | Rezolved | Low | Mobile responsive design | Navid | 80 | Client side | Rezolved
8 | Rezolved | Low | Security measures | Navid | 100 | Both | Problem
9 | Rezolved | Medium | Comment code | Ligia/Navid | 100 | Both
| Rezolved | Low | Browser compatibility | Navid | 100 | Testing | Planning
| New | Low | Social media sharing | Navid | 0 | Client side | Server side
| Rezolved | Low | Own Diamond Dash | Navid | 100 | Both | Client side
| New | Low | Graphical statistics for developers | -incomplete: because matplotlib was too heavy for Heroku | 75 | Server side | Testing
| Rezolved | High | Login, logout and register developer with UI | NAVID | 100 | Both
| Rezolved | High | Login, logout and register player with UI | NAVID | 100 | Both
| Rezolved | Medium | Email validation | Navid | 100 | Both
| Rezolved | Medium | security restrictions player | navid | 100 | Server side
| Rezolved | Medium | security restrictions developer | navid | 100 | Server side
| Rezolved | Medium | deploy to heroku and settings | navid | 90 | Testing
| Rezolved | Medium | front end - css/bootstrap/js | navid | 100 | Client side
| Rezolved | High | Buy games - payment | navid | 100 | Both
| Rezolved | High | Games category | navid | 100 | Both
| Rezolved | High | Search functionality | navid | 100 | Both
| Rezolved | High | Add a game (URL) and set price for that game and manage that game | navid | 100 | Both
| Rezolved | High | game inventory and sales statistics | navid | 100 | Both
| Rezolved | High | Messages from service to the game | Ligia | 100 | Client side
| Rezolved | High | submit score functionality | Ligia | 100 | Both
| Rezolved | High | save feature | Ligia | 100 | Both
| Rezolved | High | load feature | Ligia | 100 | Both
| Rezolved | High | Service interraction degugging and testing with variables | Ligia | 100 | Testing
| In progress | Medium | documentation | Ligia | 100 | Planning and Testing
| In progress | Medium | project management | Ligia+Navid | 90 | Planning
| In progress | Medium | team meetings | Ligia+Navid | 80 | Planning
| In progress | Medium | demo preparations | Ligia + Navid | 10 | Planning and Testing
Note on E1: we should write as many as we can now, and then we should start taking them and writing names -Ligia Gaspar
Note on E1: i wrote also connections as some tasks will also have some connections with others and they should be pointed there with id -Ligia Gaspar