## Sheet1
ID | STATUS | PRIORITY | TASK | PERSON | Done% | Category
1 | Rezolved | High | project plan | Ligia | 100 | Planning | High
2 | In progress | Medium | use cases | Ligia | 20 | Planning | Medium
3 | Rezolved | Medium | create project in git | Navid | 100 | Planning | Low
4 | Rezolved | High | database model | Navid | 100 | Planning
5 | New | High | url model | Navid | 60 | Planning | New
6 | In progress | High | UI Sketching | Ligia/Navid | 90 | Planning | In progress
7 | In progress | Low | Mobile responsive design | Navid | 80 | Client side | Rezolved
8 | Rezolved | Low | Security measures | Navid | 100 | Server side | Problem
9 | Rezolved | Medium | Comment code | Ligia/Navid | 100 | Both
| Rezolved | Low | Browser compatibility | Navid | 100 | Testing | Planning
| New | Low | Social media sharing | Navid | 0 | Client side | Server side
| Rezolved | Low | Own Diamond Dash | Navid | 100 | Client side | Client side
| New | Low | Graphical statistics for developers | -incomplete: because matplotlib was too heavy for Heroku | 10 | Server side | Testing
| In progress | High | Login, logout and register developer with UI | NAVID | 70 | Server side
| In progress | High | Login, logout and register player with UI | NAVID | 70 | Server side
| Rezolved | Medium | Email validation | Navid | 100 | Server side
| In progress | Medium | security restrictions player | navid | 90 | Server side
| In progress | Medium | security restrictions developer | navid | 90 | Server side
| In progress | Medium | deploy to heroku and settings | navid | 80 | Testing
| Rezolved | Medium | front end - css part | navid/bahareh | 100 | Client side
| Rezolved | High | Buy games - payment | navid | 100 | Server side
| Rezolved | High | Games category | navid | 100 | Server side
| Rezolved | High | Search functionality | navid | 100 | Server side
| Rezolved | High | Add a game (URL) and set price for that game and manage that game | navid | 100 | Both
| Rezolved | High | game inventory and sales statistics | navid | 100 | Server side
| Rezolved | High | Messages from service to the game | Ligia | 100 | Client side
| Rezolved | High | submit score functionality | Ligia | 100 | Both
| Rezolved | High | save feature | Ligia | 100 | Both
| Rezolved | High | load feature | Ligia | 100 | Both
| Rezolved | High | Service interraction degugging and testing with variables | Ligia | 100 | Testing
| In progress | Medium | documentation | Ligia | 50 | Planning and Testing
| In progress | Medium | project management | Ligia+Navid | 90 | Planning
| In progress | Medium | team meetings | Ligia+Navid | 80 | Planning
| In progress | Medium | demo preparations | Ligia + Navid | 10 | Planning and Testing
The TASKS BACKLOG is going to be complete by the end of the project. The google docs spredsheet for the tasks backlog is still in development at the address: https://docs.google.com/spreadsheets/d/1IdPMNIqXZPcSzgsmlt6LVJtAPlYX20DWWfK3c2osuUE/edit?usp=sharing
Note on E1: we should write as many as we can now, and then we should start taking them and writing names -Ligia Gaspar

## Sheet2
User stories
Player | I want to log in the system
I want to see the list of games available and seach by category
I want to buy a game from that list
I want to have a personal page with all the games assigned to me
I want to play a game from my personal list
I want to see the general high score for the game, my high score and the score that I am getting now by pushing a button
Developer